## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2211-swen610-01-team-2-rhinodonkey
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | MF 10/4, SH 10/4, RK 10/4, SK 10/4
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | MF 10/4, SH 10/4, RK 10/4, SK 10/4
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | MF 10/4, SH 10/4, RK 10/4, SK 10/4
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | MF 10/4, SH 10/4, RK 10/4, SK 10/4
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | MF 10/4, SH 10/4, RK 10/4, SK 10/4
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | MF 10/4, SH 10/4, RK 10/4, SK 10/4
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | MF 10/4, SH 10/4, RK 10/4, SK 10/4
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | MF 10/4, SH 10/4, RK 10/4, SK 10/4
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | MF 10/4, SH 10/4, RK 10/4, SK 10/4
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | MF 10/4, SH 10/4, RK 10/4, SK 10/4
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | MF 10/4, SH 10/4, RK 10/4, SK 10/4
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | MF 10/4, SH 10/4, RK 10/4, SK 10/4
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | MF 10/4, SH 10/4, RK 10/4, SK 10/4
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | MF 10/5, SH 10/5, RK 10/5, SK 10/5
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | MF 10/4, SH 10/4, RK 10/4, SK 10/4
A single piece can move diagonally forward away from the player to a vacant space. | Given that I want to make a move when I move 1 square diagonally then I expect the piece to move to that space |  |  | Pass | MF 10/24, SH 10/24, RK 10/24, SK 10/24
| Given that it is the opponent's turn when I try to make a move then I cannot move the piece |  |  | Pass | MF 10/24, SH 10/24, RK 10/24, SK 10/24
| Given that I want to make a move when I move the piece then I expect to move only to adjacent spaces |  |  | Pass | MF 10/24, SH 10/24, RK 10/24, SK 10/24
| Give that I want to make a move when I move the piece backwards diagonally then the piece is not droppable |  |  | Pass | MF 10/24, SH 10/24, RK 10/24, SK 10/24
A piece needs to jump diagonally over the opponent’s piece to a vacant dark space so that it can capture the opponent’s piece. The piece can only jump over opponent’s pieces. | Given that my piece is adjacent to an opponent's piece when I move the piece towards the opponent's piece then I expect to be able to move to a vacant space diagonally behind the opponent's piece. |  |  | Pass | MF 10/24, SH 10/24, RK 10/24, SK 10/24
| Given that my piece jumps over the opponent's piece when I capture the opponent's piece then the captured piece disappears from the board. |  |  | Pass | MF 10/24, SH 10/24, RK 10/24, SK 10/24
| Given that an opponent's piece is placed diagonally behind my piece when I move the piece backward to capture the opponent's piece then my piece is not droppable |  |  | Pass | MF 10/24, SH 10/24, RK 10/24, SK 10/24
A piece needs to be able to jump from a dark space over an opponent’s piece to a vacant dark space multiple times in the same turn to capture multiple pieces. | Given that I captured an opponent's piece and there are more available pieces to capture when I move the same piece again to capture then I capture an additional opponent's piece |  |  | Pass | MF 10/24, SH 10/24, RK 10/24, SK 10/24
| Given that I captured an opponent's piece and there are more available pieces to capture diagonally behind this piece when I move the same piece backward to capture then my piece is not droppable |  |  | Pass | MF 10/24, SH 10/24, RK 10/24, SK 10/24
A piece must be able to be upgraded to a king by reaching the furthest row, this allows a piece to move both away from the player or towards a player. | Given that my piece is adjacent to an empty space in the farthest row when I move my piece to the farthest row on the board then my piece becomes a king with a visual change |  |  | Pass | MF 10/24, SH 10/24, RK 10/24, SK 10/24
| Given that my piece is a king when I move my piece backward diagonally then my king piece is droppable |  |  | Pass | MF 10/24, SH 10/24, RK 10/24, SK 10/24
| Given that my piece is a king when I jump with my king piece backward diagonally then my king piece is droppable |  |  | Pass | MF 10/24, SH 10/24, RK 10/24, SK 10/24
| Given that my non-king piece is adjacent to an opponent's king piece when I jump over the opponent's king then I expect to be able to capture the opponent's king. |  |  | Pass | MF 10/24, SH 10/24, RK 10/24, SK 10/24
The application needs to recognize when a player has no pieces left on the board to end the game and announce that the winner is the player with pieces remaining. | Given that it is my turn when I capture an opponent's last piece then I expect the game to end and display the winner's name |  |  | Pass | MF 10/24, SH 10/24, RK 10/24, SK 10/24
As a player I want to sign out so that I cannot be invited to games | Given that I am logged in when I am in the app then the sign out option is available
Given that I am logged in when I choose to sign out then my name is removed from the list of online players
A piece is required to jump an opponent’s piece if there is the opportunity for a piece to jump. Multiple jumps must be completed as well as the piece cannot stop in the middle of the jump. The player may choose which jump to make in the case of several options. | Given that it is my turn when there is a jumpable piece then the game requires the piece to make the jump
Given that I have jumped an opposing piece when there is another jumpable piece the game requires the piece to make the jump
A game needs to make it evident that it is the player’s turn so that they know to go in and take their turn. | Given I am in a game when it is my turn then the game will notify me
Given I am in a game when it is not my turn then the game will tell me it is my opponent's turn
The Player must be able to resign (forfeit) any game he/she is playing. | Given that I am currently in a game when I am looking at the screen there is the option to resign
Given that I am currently in a game when I select the option to resign the game is ended for both players.
Given that I am currently in a game when I select the option to resign then the other player is declared the winner
A player must be able to see a list of what games are currently happening so that they can choose to view the game. | Given that I have signed in when I select a game then I should be able to spectate an on going game.
Given that I have signed in when I view the home page then I should be able to see a list of all ongoing game.
Given that I have signed in when I spectate my own game then I should not be able to view a game.
A player must not be able to interfere with a game that they are observing. | Given that I am spectating a game when I move the pieces then the pieces should not be draggable.
Given that I am spectating a game, when I press the resign button then neither of the players are resigned.
Given that I am logged in when I spectate a game then I should not be able to see the submit button and backup button.
A player must be able to leave a game that they are observing so that they can play a game or observe a different game. | Given that I spectate a game, when I exit the game, then I should be able to view a list of all ongoing games to spectate.
Given that I spectate a game, when I exit the game, then I should be able to view a list of available players to start a game.
Given that I spectate a game, when I exit the game, then I should be able to spectate the game that I just exited.
Given that I am spectating a game when the game ends then I should be directed to the lobby.
Given that I am spectating a game when a player resigns then I should be directed to the lobby.